## Sheet1
Sr No | Title Name | From | To | Status
1 | Requirements Gathering and Analysing | 2025-06-23 | 2025-06-28 | 100%
2 | Project Setup | 2025-06-29 | 2025-07-05 | 100%
3 | Database Schema Design | 2025-07-06 | 2025-07-12 | 100%
4 | Home Page | 2025-07-13 | 2025-07-19 | 100%
5 | Other Frontend Pages and login and signup page | 2025-07-20 | 2025-07-26 | 100%
6 | Testing of Pages and Service creation of otp verificationon using email, User Model Creation and Pages Controllers | 2025-07-27 | 2025-08-02 | 100%
7 | Admin module(User verification and Painting approval from admin) Seller module ( list painting and apply for auction) and Home page (Upcomming Auctions will be Display) | 2025-08-03 | 2025-08-09 | 100%
8 | Seller Module(Listing Stauts and Filterring using Search) | 2025-08-10 | 2025-08-16 | 100%
9 | User Module(Prview of Artworks) and Dynamic dasboard for Admin and Seller's and Updatation Documenation of Project | 2025-08-17 | 2025-08-23 | 100%